Homework 5

RACI

| Task/Role | DEV | PM | UX | DEVOPS | QA |
| --- | --- | --- | --- | --- | --- |
| Requirements | C | A | C | C | C |
| Design | R | A | C | R | I |
| Implementation | R | C | C | C | C |
| System Testing | C | I | C | C | R |
| Release | I | C | I | C | I |

Roles – Company Name

DEV: Rosin Technologies Inc.

PM: John Smith

UX: Sally Designs

DEVOPS: Skynet Developers

QA: Space City Techs

Resource & Cost Plan

- Parking Garage App (7-month project) – worked bottom-up

- Team assumptions and per-role cost (hours*rate)

  - PM:  (1,213 hours * $70/hr) = 84,910

  - Developers:  (1,213 hours * $85/hr) = 103,105

  - UX:  (1,213 hours * $75/hr) = 90,975

  - DEVOPS: (1,213 hours * $85) =  103,105

  - QA: (1,213 hours * $55/hr) = 66,715

  - Labor subtotal = $448, 810

  - Infrastructure and other costs = Cloud 5500/month * 7 = 38,500; Licenses = 55,000; APIs = 25,000; Security = 45,000; Hardware = 30,000; Training = 16,000 subtotal = 209,500

  - Overhead/Benefits (25% of labor) = 0.25 * 448,810 = 112,202.5

  - Total before contingency = 448,810 + 209,500 + 112,202.50 = 770,512.50

  - Contingency (15%) = 0.15 * 770,512.50 = 115,576.88

  - Grand total = 770,512.50 + 115,576.88 = 886,089.37 ($886k)

Cashflow Table

| Month | Labor | Infrastructure | Licenses | Overhead/Benefits (25% of labor) | Contingency (15%) | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Month 1 | 64,115.71 | 22,071.43 | 7,857.14 | 16,028.93 | 16,510.98 | 126,584.19 |
| Month 2 | 64,115.71 | 22,071.43 | 7,857.14 | 16,028.93 | 16,510.98 | 126,584.19 |
| Month 3 | 64,115.71 | 22,071.43 | 7,857.14 | 16,028.93 | 16,510.98 | 126,584.19 |
| Month 4 | 64,115.71 | 22,071.43 | 7,857.14 | 16,028.93 | 16,510.98 | 126,584.19 |
| Month 5 | 64,115.71 | 22,071.43 | 7,857.14 | 16,028.93 | 16,510.98 | 126,584.19 |
| Month 6 | 64,115.71 | 22,071.43 | 7,857.14 | 16,028.93 | 16,510.98 | 126,584.19 |
| Month 7 | 64,115.71 | 22,071.43 | 7,857.14 | 16,028.93 | 16,510.98 | 126,584.19 |
| Total | 448,810 | 154,500 | 55,000 | 112,202.50 | 115,576.88 | 886,089.37 |